FEDERAL DEMOCRATIC REPUBLIC OF ETHIOPIA

Response – Recovery – Resilience for Conflict-Affected

Communities in Ethiopia (3R-4-CACE)

(P177233)

ADDITIONAL FINANCING (AF2)

ENVIRONMENTAL and SOCIAL

COMMITMENT PLAN (ESCP)

For APPRAISAL

March 2026

ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN

- The Federal Democratic Republic of Ethiopia (the Recipient) is implementing the Response – Recovery –Resilience for Conflict-Affected Communities Project (3R-4-CACE) (P177233) (the Project), with the involvement of the Ministry of Finance (MoF), Ministry of Women and Social Affairs (MoWSA), Ethiopia Disaster Risk Management Commission (EDRMC), Ministry of Health, Ministry of Education, Ministry of Water and Energy, and Ministry of Agriculture, as set out in the “Original”, “First Additional”, and “Second Additional” Financing Agreements. The International Development Association (IDA) (the Association) has agreed to provide the original and additional financing for the project as set out in the agreements. This ESCP supersedes previous versions of the ESCP for the Project and shall apply both to the original and the additional financing for the Project referred to above .

- The Recipient shall ensure that the Project is carried out in accordance with the Environmental and Social Standards (ESSs) and this Environmental and Social Commitment Plan (ESCP), in a manner acceptable to the Association. The ESCP is a part of the Agreements. Unless otherwise defined in this ESCP, capitalized terms used in this ESCP have the meanings ascribed to them in the Agreements.

- Without limitation to the foregoing, this ESCP sets out material measures and actions that the Recipient shall carry out or cause to be carried out, including, as applicable, their respective timeframes; institutional, staffing, training, monitoring and reporting arrangements; and grievance management. The ESCP also sets out the environmental and social (E&S) documents that shall be updated, consulted, disclosed and implemented under the Project, consistent with the ESSs, in form and substance acceptable to the Association. Said E&S documents may be revised from time to time with prior written agreement by the Association. As provided for under the referred Agreements, the Recipient shall ensure that there are sufficient funds available to cover the costs of implementing the ESCP.

- As agreed by the Association and the Recipient, this ESCP will be revised from time to time, if necessary, to reflect adaptive management of Project changes or unforeseen circumstances or in response to Project performance. In such circumstances, the Association and the Recipient agree to update the ESCP to reflect these changes through an exchange of letters signed between the Association and the Recipient’s Representative specified in the Agreements. The Recipient shall promptly disclose the updated ESCP.

- The subsection on “Indicators for Implementation Readiness” below identifies the actions and measures to be monitored to assess Project readiness to begin implementation in accordance with this ESCP. Nevertheless, all actions and measures in this ESCP shall be implemented as set out in the “Timeframe” column below irrespective of whether they are listed in the referred subsection.

| MATERIAL MEASURES AND ACTIONS |  | TIMEFRAME | RESPONSIBLE ENTITY |
| --- | --- | --- | --- |
| IMPLEMENTATION ARRANGEMENTS AND CAPACITY SUPPORT |  |  |  |
| A | ORGANIZATIONAL STRUCTURE 1. Maintain Federal Project Coordination Unit (FPCU) at the national level within the MoF and Project Implementation Units (PIUs) at the MoWSA and regional levels. The FPCU/PIU shall include qualified staff and resources to support management of environmental, social, health and safety (E&S) risks and impacts of the Project, including one Environmental Specialist, one Social Specialist, and one SEA/SH specialist. | Maintain the FPCU/PIUs and these positions throughout Project implementation. | FPCU/FPIU |
| B | CAPACITY BUILDING PLAN/MEASURES Capacity building training for Project staff, stakeholders, communities and Project workers on occupational health and safety specific requirements of the ESSs/ESF, the ESMF, Environmental and Social screening and Site-specific instrument preparation SEA/ SH and response mechanism/Risk management Grievance Redress Mechanism including proper handling of SEA/SH cases Security Risk Assessment and Management Plan (SRA&MP), as relevant and necessary to implement the Project in accordance with the ESSs. | Throughout project implementation. | FPCU/FPIU |
| MONITORING AND REPORTING |  |  |  |
| C | REGULAR REPORTING Prepare and submit to the Association regular monitoring reports on the environmental, social, health and safety (E&S) performance of the Project. The reports shall include: - Status of preparation and implementation of E&S documents required under the ESCP. - Summary of stakeholder engagement activities carried out as per the Stakeholder Engagement Plan. - Complaints submitted to the grievance mechanism(s), the grievance log, and progress made in resolving them. - E&S performance of contractors and subcontractors as reported through [monthly] contractors’ and supervision firms’ reports. - Number and status of resolution of incidents and accidents reported under action E below. | Submit quarterly and annual reports to the Association throughout Project implementation Submit each report to the Association no later than 15 days after the end of each reporting period]. | FPCU/FPIU |
| D | CONTRACTORS’ MONTHLY REPORTS Require contractors and supervising firms to provide monthly monitoring reports on E&S performance in accordance with the metrics specified in the respective bidding documents and contracts and submit such reports to the Association | Submit the monthly reports to the Association upon request OR as annexes to the reports to be submitted under action C above. | /FPCU/FPIU |
| E | INCIDENTS AND ACCIDENTS Notify the Association if any incident or accident relating to the project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers, including those resulting in death or significant injury to workers or the public; acts of violence, discrimination or protest; unforeseen impacts to cultural heritage or biodiversity resources; pollution of the environment; dam failure; forced or child labor; displacement without due process (forced eviction); allegations of sexual exploitation or abuse (SEA), or sexual harassment (SH); or disease outbreaks. Provide available details of the incident or accident to the Association upon request. Arrange for an appropriate review of the incident or accident to establish its immediate, underlying and root causes. Prepare, agree with the Association, and implement a Corrective Action Plan that sets out the measures and actions to be taken to address the incident or accident and prevent its recurrence. | Notify the Association no later than 48 hours after learning of the incident or accident. Provide available details upon request. SEA/SH cases shall be reported within 24 hours to the Association. . Incident report shall be provided to the Association in line with the procedures outlined in the SEA/SH prevention and response action plan Provide review report and Corrective Action Plan to the Association no later than 10 days following the submission of the initial notice, unless a different timeframe is agreed to in writing by the [Bank/Association]. | FPCU/FPIU |
| ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS |  |  |  |
| 1.1 | ENVIRONMENTAL AND SOCIAL ASSESSMENTS AND/OR PLANS 1.Prepare and implement an Environmental and Social Impact Assessment (ESIA), and corresponding Environmental and Social Management Plan (ESMP) for substantial and Moderate risk sub projects, consistent with the relevant ESSs. 2.Prepare and implement Resettlement Plans or Abbreviated Resettlement Plans. | 1. Prepare the ESIA and ESMP prior to construction work commencement and thereafter implement the ESIA and ESMP throughout Project implementation. 2. RAPs and ARAPs shall be prepared and implemented prior to any land impacts of respective subprojects. | FPCU/FPIU/RPCU/RPIU/ |
| 1.2 | MANAGEMENT OF CONTRACTORS Incorporate the relevant aspects of the ESCP, including, inter alia, the Labor Management Procedures, and code of conduct, into the E&S specifications of the procurement documents and contracts with contractors and supervising firms. Thereafter ensure that the contractors and supervising firms comply and that they require their subcontractors to comply with the E&S specifications of their respective contracts. Provide copies of the relevant contracts with contractors/subcontractors and supervision firms to the Association. | As part of the preparation of procurement documents and respective contracts. Supervise contractors throughout Project implementation. Copies of relevant contracts provided to the Association upon request. | FPCU/FPIU/RPCU/RPIU/ |
| 1.3 | TECHNICAL ASSISTANCE Carry out the consultancies, studies (including feasibility studies, if applicable), capacity building, training, and any other technical assistance activities under the Project in accordance with terms of reference acceptable to the Association, that are consistent with the ESSs. Thereafter prepare and finalize the outputs of such activities in compliance with the terms of reference. | Throughout Project implementation. | FPCU/FPIU |
| 1.4 | CONTINGENT [EMERGENCY] [EARLY] RESPONSE FINANCING 1. Ensure that the [insert name of CERC Manual as specified the legal agreement includes a description of the E&S assessment and management arrangements [including, if applicable, insert name of any CERC-ESMF/ESMF Addendum that will be included or referred to in the CERC Manual for the implementation of [name of CERC component, e.g., CERC Part], in accordance with the ESSs. 2. Implement the E&S provisions of the CERC Manual [including, if applicable, the CERC-ESMF/ESMF Addendum, and any assessments and plans required therein]. |  |  |
| ESS 2: LABOR AND WORKING CONDITIONS |  |  |  |
| 2.1 | LABOR MANAGEMENT PROCEDURE Adopt and implement the Labor Management Procedures (LMP) for the Project | Implement the LMP throughout Project implementation. | FPCU/FPIU |
| 2.2 | OCCUPATIONAL HEALTH AND SAFETY MANAGEMENT PLAN Prepare and implement an OHS Management Plan to assess and manage the OHS risks and impacts of the Project. Require contractors and subcontractors to prepare and implement OHS Management Measures or Plan in accordance with ESMF. | Prepare the OHS Management Measures or Plan prior to any construction activity on the ground and thereafter implement the measures or plan throughout Project implementation. | FPCU/FPIU/RPCU/RPIU/WPCT |
| 2.3 | GRIEVANCE MECHANISM FOR PROJECT WORKERS Operate the grievance mechanism for Project workers, as described in the LMP and consistent with ESS2. | Maintain and operate the grievance mechanism throughout Project implementation. | FPCU/FPIU/RPCU/RPIU/WPCT |
| ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT |  |  |  |
| 3.1 | WASTE MANAGEMENT PLAN Prepare and implement a Waste Management Plan (WMP), as part of the ESMP prepared for the Project, to manage hazardous and non-hazardous wastes, consistent with ESS3. | Prepare the WMP prior to commencement of subproject activities and thereafter implement the WMP throughout Project implementation]. | FPCU/FPIU/RPCU/RPIU/WPCT |
| 3.2 | RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT Incorporate resource efficiency and pollution prevention and management measures in the ESMP to be prepared under action 1.1 above. | Same timeframe as for the preparation and implementation of the ESMP | FPCU/FPIU/RPCU/RPIU/WPCT |
| ESS 4: COMMUNITY HEALTH AND SAFETY |  |  |  |
| 4.1 | TRAFFIC AND ROAD SAFETY Incorporate measures to manage traffic and road safety risks as required in the ESMP to be prepared under action 1.1 above. | Same timeframe as for the preparation and implementation of the ESMP | FPCU/FPIU/RPCU/RPIU/WPCT |
| 4.2 | COMMUNITY HEALTH AND SAFETY Assess and manage specific risks and impacts to the community arising from Project activities. e.g., behavior of Project workers, risks of labor influx, response to emergency situations, and include mitigation measures in the ESMPs to be prepared in accordance with the ESMF. | Same timeframe as for the preparation and implementation of the ESMP | FPCU/FPIU/RPCU/RPIU/WPCT |
| 4.3 | SEA AND SH RISKS Adopt and implement the SEA/SH Action Plan of the Project, to assess and manage the risks of SEA and SH. Maintain dedicated reporting channels for cases of SEA/SH and other forms of project-related GBV. If deemed necessary, a dedicated SEA/SH GRM will be established. Reporting and response protocols, including guidelines for provision of confidential, survivor-centered care, shall be detailed in the SEA/SH Prevention and Response Action Plan. | Implement the SEA/SH Action Plan throughout Project implementation. | FPCU/FPIU/RPCU/RPIU/WPCT |
| 4.4 | SECURITY MANAGEMENT Assess and implement measures to manage the security risks of the Project, including the risks of engaging security personnel to safeguard project workers, sites, assets, and activities Adopt and implement the Security Risk Assessment and Management Plan (SRA& SRMP) consistent with the requirements of ESS4, in a manner acceptable to the Association to assess and address security risks related to the Project, including those relating to the involvement of public and private security personnel, to minimize the risk of conflict and insecurity in targeted regions. | Implement the SEA/SH Action Plan throughout Project implementation. | FPCU/FPIU/RPCU/RPIU/WPCT |
| ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT [ |  |  |  |
| 5.1 | RESETTLEMENT [FRAMEWORK] [PLAN] or [PLANS] 1. Adopt and implement the Resettlement Policy Framework (RPF) for the Project, consistent with ESS5. 2. Prepare and implement a Resettlement Plan (RP) or a Livelihood Restoration Plan (LRP) for each activity under the Project for such RP or LRP is required, as set out in the RPF and consistent with ESS5. | 1) Implement the RPF throughout Project implementation 2) RAPs and ARAPs will be prepared and implemented prior to acquiring land and commencing civil works. | FPCU/FPIU/RPCU/RPIU/WPCT |
| ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES |  |  |  |
| 6.1 | BIODIVERSITY RISKS AND IMPACTS ESMF includes principles and procedures for subproject screening. Based on the screening result, those subproject activities that would cause impacts on natural habitats (including critical habitats) relevant to ESS6 will be excluded and will not be financed under the Project. | The screening process shall take place prior to the approval of each subproject and prior to commencing implementation of the sub-project during annual planning of the project | FPCU/FPIU/RPCU/RPIU/WPCT |
| ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES [ |  |  |  |
| 7.1 | INDIGENOUS PEOPLES [FRAMEWORK] [PLAN] or [PLANS] Adopt and implement the social assessment and social development plan( SA/SDP) of the Project, in a manner acceptable to the Association. | Implement the SA/SDP throughout Project implementation | FPCU/FPIU/RPCU/RPIU/WPCT |
| ESS 8: CULTURAL HERITAGE |  |  |  |
| 8.1 | CULTURAL HERITAGE RISKS AND IMPACTS Adopt and implement the Chance Find procedure in the ESMF developed for the Project in accordance with ESS8. | Chance Find procedure integrated in sub-project ESMPs and implemented and monitored throughout Project implementation. | FPCU/FPIU/RPCU/RPIU/WPCT |
| ESS 9: FINANCIAL INTERMEDIARIES |  |  |  |
| ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE |  |  |  |
| 10.1 | STAKEHOLDER ENGAGEMENT PLAN Update and implement the Stakeholder Engagement Plan (SEP) for the Project, consistent with ESS10, which shall include measures to, inter alia, provide stakeholders with timely, relevant, understandable and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination and intimidation. | Update the SEP prior to AF appraisal | FPCU |
| 10.2 | PROJECT GRIEVANCE MECHANISM Maintain, and operate an accessible grievance mechanism, to receive and facilitate resolution of concerns and grievances in relation to the Project, promptly and effectively, in a transparent manner that is culturally appropriate and readily accessible to all Project-affected parties, at no cost and without retribution, including concerns and grievances filed anonymously, in a manner consistent with ESS10. The grievance mechanism shall be equipped to receive, register, and facilitate the resolution of SEA/SH complaints, including through the referral of survivors to relevant gender-based violence service providers, all in a safe, confidential, and survivor-centered manner. | Maintain and operate the mechanism throughout Project implementation | FPCU/FPIU/RPCU/RPIU/WPCT |
| INDICATORS FOR IMPLEMENTATION READINESS |  |  |  |
| The following actions are indicators for implementation readiness: - Maintain Federal Project Coordination Unit (FPCU) at the national level within the MoF and Project Implementation Units (PIUs) at the MoWSA and regional levels with qualified staff and resources - Update and disclose the Stakeholder Engagement Plan (SEP) before appraisal |  |  |  |